## Prioritized Backlog
# | Issue | Category | Agent | Priority | Effort | Impact | Sprint | File(s) | Description & Fix | Status
1 | Remove hardcoded Supabase credentials | Security | Auditor+Security | P0 | S (2h) | Critical | 1 | lib/constants/supabase_config.dart | Supabase URL and anon key are hardcoded in source. The JWT exposes project ref, role, and expiry. Move to --dart-define build flags: const supabaseUrl = String.fromEnvironment('SUPABASE_URL'); const supabaseAnonKey = String.fromEnvironment('SUPABASE_ANON_KEY'); Update build commands and CI accordingly. Add supabase_config.dart to .gitignore if keeping a local dev fallback. | Open
2 | Server-side bill number generation | Data Integrity | Logic+Arch | P0 | M (6h) | Critical | 1 | lib/services/bill_number_service.dart, Supabase Edge Function (new) | BillNumberService uses an in-memory counter. Two devices can generate the same bill number simultaneously, and dedup on sync silently drops one bill. Fix: Create a Supabase Edge Function or DB sequence that atomically generates bill numbers per business. Call it from completeBill() before saving. Remove client-side counter as primary source. | Open
3 | Server-side subscription limit enforcement | Security | Logic+Arch | P0 | M (8h) | Critical | 1 | lib/providers/subscription_provider.dart, Supabase RLS/Edge Fn (new) | canAddBill is checked client-side only; trivially bypassable. increment_bill_count RPC runs AFTER bill creation. Fix: Move bill count check to a Supabase Edge Function or RLS policy that rejects inserts when limit is reached. Return error to client if limit exceeded. | Open
4 | Fix deleteBill() fallback bug | Bug | Auditor | P0 | S (1h) | Critical | 1 | lib/providers/bill_provider.dart (line 600-609) | deleteBill() uses firstWhere with orElse: () => _bills.first. If billNumber not found, it deletes the FIRST bill in the list — wrong bill. Fix: Use firstWhereOrNull pattern; if null, return early without deleting. Code: final bill = _bills.cast<Bill?>().firstWhere((b) => b?.billNumber == billNumber, orElse: () => null); if (bill == null) return; | Open
5 | Wrap completeBill() in DB transaction | Data Integrity | Logic+Arch | P0 | M (6h) | Critical | 1 | lib/providers/bill_provider.dart (line 381-527) | completeBill() saves the bill, THEN decrements stock, THEN updates credit. If app crashes between steps, data is inconsistent. Fix: Use Supabase RPC function that atomically: (1) saves bill, (2) decrements stock, (3) updates credit, (4) increments bill count. If any step fails, all roll back. | Open
6 | Prevent negative stock on decrement | Data Integrity | Logic | P0 | S (2h) | Critical | 1 | lib/providers/product_provider.dart — decrementStock() | decrementStock() does not validate resulting stock >= 0. A product with 5 units can have 10 sold. Fix: Add validation: if (product.stockQuantity - quantity < 0) throw InsufficientStockException(); Also handle batch-level stock check for pharmacy products. | Open
7 | Add PIN rate limiting | Security | Security | P0 | S (3h) | Critical | 1 | lib/providers/user_provider.dart — login() | 4-digit PIN with static salt "billmaster", no lockout. 10K combinations brute-forceable in milliseconds. Fix: (1) Track failed attempts per user. (2) Lock account for 30s after 3 failures, 5min after 5, permanent after 10. (3) Show remaining attempts to user. (4) Long-term: migrate to 6-digit PIN or biometric. | Open
8 | Add error handling to syncFromDb() | Bug | Auditor | P0 | S (2h) | High | 1 | lib/providers/bill_provider.dart (line 578-598) | syncFromDb() catches ALL exceptions with empty catch block. Network failures, auth expiry, malformed data — all invisible. Fix: (1) Log the error. (2) Differentiate network vs auth vs parse errors. (3) Show user-facing message on auth expiry. (4) Retry with backoff on network failure. | Open
9 | Fix batch decrement silent success | Bug | Logic | P0 | S (2h) | High | 1 | lib/providers/product_provider.dart — decrementStock() | decrementStock with batchId: if batch not found, silently decrements main product stock without batch adjustment. Fix: If batchId provided but batch not found, throw an error or log a warning. Don't silently fall through. | Open
10 | Make all model fields immutable | Code Quality | Auditor | P1 | L (2d) | High | 2 | lib/models/product.dart, customer.dart, supplier.dart, line_item.dart, serial_number.dart, job_card.dart | Product.stockQuantity, Customer.outstandingBalance/advanceBalance, Supplier.outstandingPayable, LineItem.quantity/discountPercent, SerialNumber.status/billId, JobLineItem.quantity/unitPrice are mutable. State can change without notifyListeners(). Fix: Make all fields final. Add copyWith() where missing. Update providers to create new instances instead of mutating. | Open
11 | Add GST rounding to 2 decimal places | Business Logic | Logic | P1 | S (2h) | High | 2 | lib/services/gst_calculator.dart | Floating-point arithmetic accumulates rounding errors. Indian invoicing requires amounts rounded to nearest paisa. Fix: Add explicit rounding after every calculation: (value * 100).round() / 100. Apply in cgst(), sgst(), igst(), taxableAmount(), grandTotal(). | Open
12 | Track GST breakdown on returns | Business Logic | Logic | P1 | M (4h) | High | 2 | lib/models/return_line_item.dart, sales_return.dart | ReturnLineItem.refundAmount is a lump sum without CGST/SGST/IGST breakdown. GSTR-1 filing requires reversed tax amounts separately. Fix: Add cgst, sgst, igst fields to ReturnLineItem and SalesReturn. Calculate from original bill's tax rates during return creation. | Open
13 | Validate return qty <= original bill qty | Business Logic | Logic | P1 | S (2h) | High | 2 | lib/providers/return_provider.dart — addReturn() | No server-side or provider-level check that returned quantity doesn't exceed original bill quantity. Bug in UI could create impossible returns. Fix: In addReturn(), look up original bill, sum existing returns for same bill/product, reject if total returned > original qty. | Open
14 | Add server-side RLS for role enforcement | Security | Security+Arch | P1 | L (2d) | High | 2 | Supabase dashboard (new policies) | PermissionService checks are client-side only. A modified client can bypass all role restrictions. Fix: Create Supabase RLS policies that check user role stored in app_users table. E.g., only owner role can delete bills, only owner/manager can adjust stock. | Open
15 | Encrypt local state file | Security | Security | P1 | M (4h) | High | 2 | lib/services/local_storage_service.dart | app_state.json stored unencrypted with all business data and PII. Fix: Use flutter_secure_storage for encryption key, encrypt state JSON with AES before writing. Decrypt on read. Consider using Hive with encryption instead of raw file I/O. | Open
16 | Extract shared JSON helpers | Code Quality | Auditor | P1 | S (3h) | Medium | 2 | lib/core/utils/json_helpers.dart (new) | _asDouble(), _asInt(), _nullableInt(), _nullableDouble(), _nullableString() duplicated across 15+ model files. Fix: Create a shared JsonHelpers class with static methods. Update all models to use the shared helpers. | Open
17 | Unify payment mode enums | Code Quality | Auditor | P1 | M (4h) | Medium | 2 | lib/models/payment_info.dart, expense.dart, customer_payment_entry.dart | Three separate payment mode enums: PaymentMode (4 values), ExpensePaymentMode (4 values), SettlementPaymentMode (3 values). Confusing and error-prone. Fix: Create a single unified PaymentMethod enum with all modes. Add a "context" or "applicability" concept if some modes only apply in certain scenarios. | Open
18 | Extract _resetActiveState() in BillProvider | Code Quality | Auditor | P1 | S (1h) | Medium | 2 | lib/providers/bill_provider.dart | 12-field reset block duplicated 4 times (lines 424-437, 512-524, 545-555, 560-575). Fix: Extract to private _resetActiveState() method and call it from completeBill(), clearActiveBill(), clearAllBills(), replaceAllData(). | Open
19 | Add global error handler | Reliability | Auditor | P1 | M (4h) | High | 2 | lib/main.dart | No global error handler. Uncaught Flutter errors go to default handler. Fix: Add FlutterError.onError and PlatformDispatcher.onError in main(). Log errors to a service (Sentry, Crashlytics, or Supabase table). Show user-friendly error dialog for critical failures. | Open
20 | Add crash reporting service | Reliability | Security | P1 | M (4h) | High | 2 | pubspec.yaml, lib/main.dart | No crash reporting. Production crashes are invisible. Fix: Integrate Sentry (sentry_flutter) or Firebase Crashlytics. Wrap runApp in error zone. Configure breadcrumbs for state changes. | Open
21 | Fix ReportService month iteration bug | Bug | Logic | P1 | S (1h) | Medium | 2 | lib/services/report_service.dart | Month iteration uses cursor.month + 1 which overflows from December (12+1=13). Fix: Use DateTime(cursor.year, cursor.month + 1) which Dart handles correctly, but verify the logic handles year boundaries properly. | Open
22 | Add DB operation retry with backoff | Reliability | Security | P1 | M (4h) | High | 2 | lib/services/db_service.dart | Single network blip during bill save means bill in memory but not in DB. No retry. Fix: Add exponential backoff retry wrapper (3 attempts, 1s/2s/4s delays) for all Supabase operations. Queue failed operations for retry on reconnect. | Open
23 | Decouple providers with use cases | Architecture | Arch | P1 | XL (1w) | High | 3 | lib/domain/usecases/ (new directory) | BillProvider calls ProductProvider.decrementStock() and CustomerProvider.addCredit() directly. PurchaseProvider calls ProductProvider.incrementStock() and SupplierProvider.addPayable(). Fix: Create use case classes: CompleteBillUseCase, CreatePurchaseUseCase, ProcessReturnUseCase that orchestrate multi-provider operations atomically. | Open
24 | Add repository pattern | Architecture | Arch | P1 | XL (1w) | High | 3 | lib/data/repositories/ (new), lib/domain/repositories/ (new) | Providers call DbService directly, mixing state management with data access. Fix: Create abstract repository interfaces in domain/repositories/. Implement concrete repositories in data/repositories/ that wrap DbService. Inject repositories into providers. | Open
25 | Add pagination to all list screens | Performance | Perf+UX | P1 | L (3d) | High | 3 | lib/screens/bill_history_screen.dart, product_list_screen.dart, customer_tab_screen.dart, expense_list_screen.dart, purchase_list_screen.dart | All lists load entire dataset into memory. At 10K+ items = OOM. Fix: Implement cursor-based pagination with lazy loading. Load 50 items initially, fetch more on scroll. Use ListView.builder with pagination controller. | Open
26 | Optimize CashBook recalculation | Performance | Perf | P1 | M (6h) | High | 3 | lib/providers/cash_book_provider.dart | Recalculates ALL days from earliest change on any dependency update. O(n) per change, n=365+. Fix: (1) Only recalculate the specific day affected. (2) Use signature comparison to identify which day changed. (3) Lazily recalculate only when the day is viewed. | Open
27 | Replace IndexedStack with lazy tab loading | Performance | Perf | P1 | M (4h) | Medium | 3 | lib/screens/home_shell.dart | IndexedStack keeps all tabs in memory simultaneously. All providers active even for unvisited tabs. Fix: Use PageView with AutomaticKeepAliveClientMixin or a custom lazy-loading tab wrapper that only builds tabs on first visit. | Open
28 | Reduce Dashboard provider watching | Performance | Perf | P1 | M (4h) | Medium | 3 | lib/screens/dashboard_screen.dart | Dashboard watches 8 providers. Any change triggers full rebuild. Fix: (1) Use context.select() to watch only specific fields. (2) Split into sub-widgets that each watch one provider. (3) Memoize computed values (today's sales, bill count, etc.). | Open
29 | Add loading skeletons and empty states | UX | UX | P1 | L (2d) | Medium | 3 | lib/widgets/skeleton_loader.dart (new), all list screens | Screens show empty state while data loads, creating flash of "no data". Fix: Create shimmer/skeleton widgets. Show them during initial load. Differentiate between "loading" and "no data" states across all list screens. | Open
30 | Add pull-to-refresh on list screens | UX | UX | P1 | S (3h) | Medium | 3 | lib/screens/bill_history_screen.dart, product_list_screen.dart, customer_tab_screen.dart, expense_list_screen.dart | No pull-to-refresh on list screens. Users cannot manually trigger data sync. Fix: Wrap list views in RefreshIndicator. Call syncFromDb() or equivalent on refresh. | Open
31 | Add undo for destructive actions | UX | UX | P1 | M (4h) | Medium | 3 | lib/screens/product_list_screen.dart, bill_history_screen.dart | Deleting a product, clearing a bill, or deleting a customer is permanent. Fix: Show SnackBar with "Undo" action for deletions. Use a soft-delete pattern (isDeleted flag) with cleanup after 30s timeout. | Open
32 | Add Semantics widgets for accessibility | Accessibility | UX | P2 | L (3d) | Medium | 4 | All screens and widgets | No Semantics widgets anywhere. Screen readers cannot navigate the app. Fix: Add Semantics wrappers to all interactive elements. Use ExcludeSemantics for decorative elements. Test with TalkBack (Android). | Open
33 | Hindi/regional language support (i18n) | UX | UX | P2 | XL (1w) | High | 4 | lib/l10n/ (new), lib/constants/app_strings.dart | All UI text is English only. Many Indian shopkeepers prefer Hindi/Tamil/Telugu. Fix: Migrate AppStrings to Flutter l10n (intl_utils or flutter_localizations). Create .arb files for Hindi as first additional language. Add language switcher in settings. | Open
34 | Add integration tests for core flows | Testing | Auditor | P2 | XL (1w) | High | 4 | test/integration/ (new directory) | No integration tests. Critical flows untested end-to-end. Fix: Add integration tests for: (1) bill creation → stock decrement → cash book update, (2) purchase → stock increment → supplier payable, (3) return → stock restoration → credit note, (4) quotation → approval → bill conversion. | Open
35 | Add tests for untested providers | Testing | Auditor | P2 | L (3d) | High | 4 | test/ (new test files) | SubscriptionProvider, TableOrderProvider, JobCardProvider, SerialNumberProvider, AuthProvider, NavigationProvider have ZERO tests. Fix: Add unit tests for each with at least: CRUD operations, edge cases, error scenarios. | Open
36 | Add onboarding flow for new users | UX | UX | P2 | L (3d) | Medium | 4 | lib/screens/onboarding/ (new directory) | After signup, users land on empty setup screen with no guidance. Fix: Create 3-4 step onboarding: (1) Welcome + business type selection, (2) Business details, (3) First product/sample data, (4) Quick billing tutorial. | Open
37 | Add search to quotations, suppliers, job cards | UX | UX | P2 | S (3h) | Medium | 4 | lib/screens/quotation_list_screen.dart, supplier_list_screen.dart, workshop/job_card_list_screen.dart | Only bills, products, customers, and expenses have search. Quotations, suppliers, job cards, and purchases are missing search. Fix: Add SearchBarWidget to these screens with appropriate field matching. | Open
38 | Add sorting options to list screens | UX | UX | P2 | M (4h) | Low | 4 | All list screens | No sort options on any list screen. Users can't sort products by price, customers by balance, or bills by amount. Fix: Add sort dropdown/menu in AppBar: by name, date, amount, status as appropriate per screen. | Open
39 | Remove unused crypto dependency | Code Quality | Auditor | P2 | S (15m) | Low | 4 | pubspec.yaml | crypto ^3.0.6 listed but never imported anywhere. Fix: Remove from pubspec.yaml and run flutter pub get. | Open
40 | Add copyWith to Bill, PurchaseEntry, LineItem | Code Quality | Auditor | P2 | S (2h) | Low | 4 | lib/models/bill.dart, purchase_entry.dart, line_item.dart | Bill, PurchaseEntry, and LineItem lack copyWith methods, unlike other models. Fix: Add standard copyWith with optional parameters. Bill has many fields so consider a builder pattern instead. | Open
41 | Complete CashBook discrepancy feature | Feature | Logic | P2 | M (4h) | Low | 4 | lib/providers/cash_book_provider.dart | getCashDiscrepancy() always returns null — incomplete stub. Fix: Implement expected vs actual cash balance comparison. Allow user to record actual cash counted. Calculate discrepancy = actual - expected closing. | Open
42 | Migrate JSONB to relational schema | Architecture | Arch | P2 | XL (2w) | High | 5 | Supabase schema (migration), lib/services/db_service.dart | All entities stored as JSONB blobs. No foreign keys, joins, indexes, or DB-level filtering. Fix: Create proper relational tables: bills, bill_line_items, products, customers, etc. Write migration script. Update DbService to use relational queries. Add indexes on timestamp, business_id, barcode. | Open
43 | Invoice-level payment linkage | Business Logic | Logic | P2 | L (2d) | Medium | 5 | lib/providers/customer_provider.dart, lib/models/customer_payment_entry.dart | Payments reduce total outstanding but aren't linked to specific invoices. Fix: Add optional billId field to CustomerPaymentEntry. Allow payment allocation to specific invoices. Show payment status per invoice in bill history. | Open
44 | Add dark mode support | UX | UX | P2 | L (2d) | Low | 5 | lib/constants/app_colors.dart, lib/app.dart | Single light color scheme only. Fix: Create dark mode color palette. Use ColorScheme.fromSeed with brightness parameter. Add dark mode toggle in settings. Persist preference. | Open
45 | CSV injection prevention | Security | Security | P2 | S (2h) | Medium | 5 | lib/services/csv_service.dart | CSV import parses values without sanitizing formula injection (=CMD, +CMD). Fix: Prefix values starting with =, +, -, @ with a single quote. Validate/sanitize on import. | Open
46 | Add HTTPS certificate pinning | Security | Security | P2 | M (4h) | Medium | 5 | lib/services/supabase_service.dart | No certificate pinning for Supabase connections. MITM attacks possible. Fix: Use http_certificate_pinning package or custom HttpClient with pinned certificates for Supabase domain. | Open
47 | Add data backup strategy | Reliability | Security | P2 | M (6h) | Medium | 5 | lib/services/backup_service.dart (new) | Only manual export. If Supabase data corrupted and local backup stale, data is lost. Fix: Schedule automatic daily backups to local storage. Keep last 7 days. Allow restore from backup. Consider cloud backup option. | Open
48 | Add keyboard shortcuts for web | UX | UX | P2 | M (4h) | Low | 5 | lib/screens/create_bill_screen.dart, home_shell.dart | No keyboard shortcuts for desktop/web users. Fix: Add shortcuts: Ctrl+N = new bill, Ctrl+F = search, Enter = add item, Ctrl+S = save/complete, Esc = cancel. Use Shortcuts and Actions widgets. | Open
49 | Add export options to reports | Feature | UX | P2 | M (4h) | Medium | 5 | lib/screens/reports_screen.dart | No export for P&L, Sales, Inventory, Cash Flow, GST reports. Only GSTR-1 has CSV export. Fix: Add PDF and CSV export buttons to each report tab. Use ReportService data to generate formatted exports. | Open
50 | Add cheque clearing workflow | Business Logic | Logic | P2 | L (2d) | Low | 5 | lib/models/cheque.dart (new), lib/providers/cheque_provider.dart (new) | Cheque payment mode exists but no tracking, bounce handling, or clearing confirmation. Fix: Add Cheque model with: number, date, bank, amount, status (pending/cleared/bounced). Add provider and UI for cheque management. | Open
51 | Add voice input for product search | UX | UX | P3 | M (6h) | Low | 6 | lib/widgets/search_bar_widget.dart | Many shopkeepers find typing difficult. Fix: Add microphone icon to search bar. Use speech_to_text package for voice search. Convert speech to text and trigger product search. | Open
52 | Add equals/hashCode to all models | Code Quality | Auditor | P3 | L (2d) | Low | 6 | All model files | No == operator or hashCode override on any model. Collections can't properly deduplicate. Fix: Add equatable package or manually implement == and hashCode based on id field for all models. | Open
53 | Add toString() to all models | Code Quality | Auditor | P3 | S (2h) | Low | 6 | All model files | No toString() methods. Debugging shows "Instance of Product" instead of useful info. Fix: Add toString() returning key fields (id, name, amount as appropriate) to each model. | Open
54 | Make SupportTicket status an enum | Code Quality | Auditor | P3 | S (1h) | Low | 6 | lib/models/support_ticket.dart | Status stored as string "open"¦"in_progress"¦"resolved" instead of enum. Fix: Create TicketStatus enum and migrate. | Open
55 | Add toJson to SupportTicket | Code Quality | Auditor | P3 | S (30m) | Low | 6 | lib/models/support_ticket.dart | SupportTicket is read-only (no toJson). Fix: Add toJson() for consistency and offline caching support. | Open
56 | Reduce SearchBarWidget minimum chars | UX | UX | P3 | S (30m) | Low | 6 | lib/widgets/search_bar_widget.dart | Requires 2 characters minimum. Frustrating for short product names ("A4", "Tea"). Fix: Make threshold configurable via constructor parameter, defaulting to 1. | Open
57 | Add notification rate limiting | Performance | Security | P3 | S (2h) | Low | 6 | lib/services/notification_service.dart | checkLowStock shows up to 50 notifications at once. Can spam user. Fix: Limit to 5 notifications per check. Aggregate: "12 products have low stock — tap to view". | Open
58 | Fix NotificationService credit due metric | Bug | Logic | P3 | S (1h) | Low | 6 | lib/services/notification_service.dart | Credit due check uses customer creation date, not last transaction date. A customer created 90 days ago with a payment yesterday still triggers "overdue". Fix: Track last transaction/payment date and use that for overdue calculation. | Open
59 | Add iOS notification support | Feature | Security | P3 | M (4h) | Low | 6 | lib/services/_notification_mobile.dart | Only Android notification implementation exists. iOS gets no-op stub. Fix: Add iOS notification channel configuration and permissions request. | Open
60 | Optimize Expense vendor suggestions | Performance | Perf | P3 | S (1h) | Low | 6 | lib/providers/expense_provider.dart | getVendorSuggestions() iterates all expenses every call. Fix: Maintain a cached Set<String> of vendor names, updated on add/delete expense. Return cached set on request. | Open
61 | Add color-blind safe status indicators | Accessibility | UX | P3 | S (2h) | Low | 6 | lib/screens/restaurant/table_screen.dart, job_card_list_screen.dart | Color-only status indicators (red=occupied, green=available). Fix: Add icon overlays (checkmark/X) alongside colors. Use patterns or shapes as secondary indicators. | Open
62 | Clean up temp files after sharing | Performance | Security | P3 | S (1h) | Low | 6 | lib/services/invoice_share_service.dart | writeTempFile() creates files in temp directory but never cleans them up. Fix: Delete temp files after sharing completes, or schedule periodic cleanup. | Open
63 | Add file size limit on CSV import | Security | Security | P3 | S (1h) | Low | 6 | lib/screens/csv_import_screen.dart, lib/services/csv_service.dart | No file size limit on CSV import. Large files could crash the app. Fix: Check file size before parsing. Reject files > 5MB with user-friendly message. | Open
64 | Validate screenshot upload type/size | Security | Security | P3 | S (1h) | Low | 6 | lib/services/auth_service.dart | Support ticket screenshot upload accepts any file type/size. Fix: Validate MIME type (image/png, image/jpeg only) and size (< 5MB) before uploading. | Open
65 | Add page numbers to PDF invoices | Feature | UX | P3 | S (1h) | Low | 6 | lib/services/pdf_invoice_service.dart | Generated PDFs have no page numbers. Multi-page invoices are hard to organize. Fix: Add "Page X of Y" footer to generated PDFs. | Open

## Sprint Plan
Sprint | Focus | Duration | Items | Key Deliverables | Effort Estimate
Sprint 1 | Critical Fixes | Week 1-2 | #1-#9 | Supabase creds secured, server-side bill numbers, transaction wrapping, deleteBill bug fixed, negative stock prevented, PIN rate limiting, error handling | ~32 hours
Sprint 2 | Data Integrity & Quality | Week 3-4 | #10-#22 | Immutable models, GST rounding, return GST tracking, RLS policies, encrypted storage, crash reporting, global error handler, retry logic | ~6 days
Sprint 3 | Architecture & Performance | Week 5-6 | #23-#31 | Use case layer, repository pattern, pagination on all lists, CashBook optimization, lazy tabs, loading skeletons, pull-to-refresh, undo support | ~2.5 weeks
Sprint 4 | UX & Testing | Week 7-8 | #32-#41 | Accessibility (Semantics), Hindi language support, integration tests, provider tests, onboarding flow, search on all screens, sorting options | ~2.5 weeks
Sprint 5 | Schema & Polish | Week 9-11 | #42-#50 | Relational DB migration, invoice payment linkage, dark mode, CSV security, cert pinning, backups, keyboard shortcuts, report exports | ~3 weeks
Sprint 6+ | Long-term Polish | Week 12+ | #51-#65 | Voice search, model equality, toString, ticket enum, notification fixes, vendor cache, accessibility indicators, temp cleanup, CSV limits | ~2 weeks

## Summary
BillReady 2.0 — Audit Summary
Issues by Priority
Priority | Count | Total Effort
P0 — Critical | 9 | ~32 hours
P1 — Important | 22 | ~7 weeks
P2 — Nice to Have | 19 | ~5 weeks
P3 — Polish | 15 | ~2 weeks
TOTAL | 65 | ~18 weeks
Issues by Category |  |  | Issues by Agent Source
Category | Count |  | Agent | Count
Security | 9 |  | Code Auditor | 16
Data Integrity | 3 |  | Architecture | 7
Bug | 5 |  | UI/UX Design | 16
Business Logic | 5 |  | Workflow & Logic | 13
Code Quality | 10 |  | Security & Performance | 14
Architecture | 3
Performance | 7
UX | 11
Accessibility | 2
Testing | 2
Reliability | 4
Feature | 4
App Health Score
Current Score | 5.5 / 10
After Sprint 1 | 7.0 / 10
After Sprint 3 | 8.5 / 10
Target (Sprint 5+) | 9.0+ / 10